## Sheet1
Iteration 1, 4 weeks 6/16/21 - 7/14/21 | Iteration 2, 4 week 7/15/21 - 8/12/21 | Iteration 3, 4 weeks 8/13/21 - 9/10/21
UC2 points: 1 priority: 1 depends on: None | UC1 points: 2 priority: 1 depends on: UC2 | UC6 points: 1 priority: 2 depends on: UC3, UC4
UC4 points: 1 priority: 1 depends on: None | UC3 points: 1 priority: 1 depends on: UC4 | UC7 points: 1 priority: 3 depends on: UC3
| UC5 points: 1 priority: 5 depends on: UC4 | UC8 points: 1 priority: 1 depends on: UC3
UC9 points: 1 priority: 1 depends on: UC3
Based on my efforts estimations from the lab, I believe the project could be completed in 2 iterations instead of 3. I made the assumptions that each member of the team is highly experienced and will be fully dedicated to this project. So without any competing priorities for the designer, developer, and tester, they are able to have a faster turnaround time.
Risk | Risk Resolution Measures | Justification
Incorrect requirements received | All stakeholders must clearly communicate project requirements and sign-off must obtained to indicate all parties agree to what the requirements are. | Completing multiple iterations only to find out at the end of the project that incorrect information was provided could cause the project to be significantly delayed.
Personnel constraints | Ensure all team member can remain 100% dedicated to this project and are not assigned any other tasks outside of this project. | Competing projects could lead to missed deadlines on this project.
Scope Creep | Once the project scope has been signed off on, no additional features can be added. | Adding additional features to the project could increase the timeline and budget.
Interface is not user-friendly | Solicit feedback from students | Although there is a tester assigned to the project, it is important to get feedback from the actual end-users at various points in the project.
Exchange programs get canceled | University stakeholders should monitor overseas program conditions and promptly notify development team of changes. | Circumstances overseas can change for a variety of reasons and some exchange programs may have to be canceled or delayed. It is vital that students are being provided with current and accurate program information.